SECTOR PROGRAM DESIGN APPROACH

INTRODUCTION

Pre-Design Phase

Step 1 → Identify demand

Step 2 → Assess regional training and placement capacity for the target occupation

Step 3 → Recruit business partners

Step 4 → Recruit all other necessary partners

Step 5 → Develop a shared program development work plan and MOA among all of your sector program partners

Design Phase

Step 6 → Design the program

Step 7 → Develop your data collection and analysis capacity

Implement, Assess, and Adjust Phase

Step 8 → Test the program

Step 9 → Assess and redesign the program

Step 10 → Test the program again

STEP 1

Identify demand

Select an occupation to target program development.

- Develop a profile of the population you want to serve .…………………….…………………………... ☐

- Identify some occupations that might match your population’s profile  ..………... ☐

- Determine whether there are regional 
vacancies for any of those occupations ……………………………………………………………………..….……... ☐

- Select a target occupation for further exploration - talk with employers 
about their vacancies and specific entry requirements and work conditions .. ☐

- Revisit and confirm that the occupation’s 
requirements match your target population’s profile …………………………………………………... ☐

- Repeat until you have a match …………………………………………………………………………………………….……… ☐

When STEP 1 is complete, you should have identified a target occupation that:

- Has skill and work requirements that are potential matches with the needs and characteristics of your population and are attainable within a reasonable training period

- Has sufficient demand (now and for the next two to three years) in your region to make it worthwhile to develop program capacity

- Has no requirements that will present an insurmountable barrier for your population

- Has future upward mobility or career pathway potential

NOTES

STEP 2

Assess regional training and placement capacity for the target occupation

Answer this question: Is there any other organization in the region that is already successfully preparing and placing your population in your target occupation?

| IF YES | Develop a referral relationship. Determine why your population is not currently getting access to the program and develop a strategy to address this issue |
| --- | --- |
| IF NO | Proceed with program development. |

STEP 3

Recruit business partners

Answer this question: Can you identify decision makers at a minimum of

three local businesses who:

- are having difficulty filling vacancies in your target occupation

- collectively have more than sufficient vacancies in the target occupation to

make it worthwhile to develop a program

- are willing to share information about hiring requirements and how they

recruit, train and advance workers

- are aware that they have workforce needs that they cannot meet with their  current sourcing strategies

- are willing to partner with you to develop program design, play a role in

program delivery, and hire or find jobs for program graduates?

| IF YES | Proceed with program development |
| --- | --- |
| IF NO | Identify a different occupation. |

NOTES

STEP 4

Recruit all other necessary partners

Inventory your own capacity and the capacity of other organizations in your region. Seek to develop a partnership whose members, collectively, have:

Familiarity with technical, soft skill and work readiness

requirements of the target occupation.………………………………………………………..…..…………………………………... ☐

Expertise in providing technical skills training for your target occupation  ..………………... ☐

Expertise in providing basic education (literacy, numeracy, ESOL, HiSET,

technology literacy) contextualized to your target sector or occupation ….……...................... ☐

Cultural competence and relationships with your target population ………………………………... ☐

Expertise in providing work readiness services to your target population ….…………….….... ☐

Capacity to provide credentials and other certifications

required for employment in your target occupation ….………………………………………………………….…….... ☐

Capacity to provide career coaching, case management and

post-placement services contextualized to your target sector and occupation ……..…... ☐

Capacity to provide directly or provide access to support

services (child care, transportation, housing, etc.) ….……………………………………………………………….…... ☐

Capacity to design and conduct recruitment and screening for

interest, abilities and other requirements of the target occupation ….…………………………….... ☐

Expertise in developing and coordinating competency-based

subsidized work experience ….……………………………………………………………………………………………………………….……. ☐

Expertise in job development and job placement ….………………………………………………………..…………….. ☐

Successful history of providing fiscal and project management for

public and philanthropic funded initiatives ….………………………………………………………………..………………... ☐

A participant-level database or expertise in using relational

databases for program management and reporting functions …………………….……………….……... ☐

STEP 5

Develop a shared program development work plan and MOA among all of your sector program partners

Articulate a shared goal, which includes a commitment to preparing,

placing and supporting the target population in the target occupation ..……….……………... ☐

Include timelines and resource requirements …………………………………………..………..……………….………... ☐

Articulate the decision-making process and the role each

partner will play in program development. ….……............................................................................................. ☐

Identify the resources each partner organization will commit to the

program development effort and the individuals who have the authority

to represent each partner organization ……………………………………………………………………….……….……..……... ☐

NOTES

STEP 6

Design the program

1. Include all of these elements

- Recruitment and screening (essential)

- Case management and career coaching (essential)

- Support services (essential)

- Contextualized work readiness (essential)

- Contextualized literacy, numeracy, English language proficiency (depends on population needs)

- Competency-based technical skills development (essential)

- Credential or certificate preparation (depends on occupation requirements)

- Competency-based work experience (depends on population needs)

- Job development and job placement (essential)

- Post placement support (depends on population needs)

- Delivery schedule, including time of day, hours per day, number of days per week, number of weeks, number of cycles in a year, ideal number of participants in a cycle (essential)

2. Assess your draft of each component against the following questions

- Is it relevant to my target occupation requirements?

- Is it relevant and responsive to my target population characteristics/needs?

- How will I know if this component is successful?

3. Develop a project staffing plan and a project budget

- Identify the cost and other resources required to carry out each program component

- Identify the role each member of the partnership will play in each program component

- Identify the commitment requirements and resource requirements for each member of the partnership.

- Update your MOA

- Develop a strategy for providing services that cannot or should not be provided by a member of the partnership

STEP 7

Develop Your Data Collection and Analysis Capacity

Identify program quality and success measures. Consider the data you will need to assess the effectiveness of each element of your program including:

Candidate recruitment methods (consider measures such as

the relevance of the candidate pool to your screening criteria,

the % of your candidate pool that you accept into the program) ….…………………………………….... ☐

Candidate screening methods (consider participant attendance, the

program completion rate of enrollees and the placement rate of enrollees) ….……………... ☐

Case management and career coaching (consider participant

attendance, the program completion rate of enrollees, the

placement rate of enrollees and participant feedback) ….………………………………………………..………... ☐

Literacy, numeracy, English-language proficiency skill building

(consider competency-based assessment data and participant feedback) ….…………….... ☐

Technical skills instruction (consider competency-based

assessment data and participant feedback) …………….….………….................................................................. ☐

Work readiness skill building (consider competency-based

assessment data and participant feedback) ….………………………………………………………………………..…….... ☐

Work experience (consider competency-based

assessment data and participant feedback) ……………………………………………………………………….…………... ☐

Job development and job placement (consider measures such as

enrollment to placement rate, # and % of placements in the target

occupation, average placement wage, employer-provided benefits,

average weekly hours of employment and employment retention) ……………………..….……….... ☐

Post-placement support (consider measures such as employment retention,

employment advancement, wage progression and participant feedback) ….……………….... ☐

Develop your data collection and analysis capacity

- Identify and develop the tools and methods you will use to collect each data element.

- Develop data analysis capacity, including a participant-level database.

- Develop data sharing agreements and protocols among partnership members and service providers that protect participant confidentiality but allow key program staff to have real-time access to essential data.

- Assign responsibility for data analysis to a qualified staff member.

NOTES

STEP 8

Test the program

For the first cycle, build in a weekly or bi-weekly review process, examining all relevant data to identify the need for immediate program adjustments.

STEP 9

Assess and redesign the program.

Build in sufficient time between the first and second cycle to allow for

program redesign before beginning recruitment and screening activities ………………….... ☐

Convene all relevant program staff and partnership members to

analyze data and identify the need for program redesign ….………………………………………….….…….... ☐

Redesign the program as needed ……………………………….….………………………………………………………………………... ☐

NOTES

STEP 10

Test the program again.

Continue to conduct frequent program review 
sessions during program implementation ……………………………………………………………………………………………………………………………………... ☐

After every cycle, convene all relevant staff and partners to 
review program data and identify the need for program redesign .….………………….……….…….... ☐

Redesign the program as needed ……………………………….….………………………………………………………………………... ☐

NOTES